## Executive Summary
ADOBE EXPERIENCE MANAGER
Edge Delivery Services Migration Estimate
Samsung DS — Semiconductor Site + Newsroom (DS CMS 이관)
SaaS Migration Estimate — Two-Site Consolidation onto AEM Edge Delivery Services
PROJECT OVERVIEW
Client: | Samsung Electronics - Device Solutions (DS)
Source Platforms: | AEM On-Premise (Semiconductor) + WordPress (Newsroom)
Target Platform: | AEM Edge Delivery Services (SaaS / Cloud)
Websites in Scope: | semiconductor.samsung.com + news.samsungsemiconductor.com
Consolidation: | Two websites merged into one at redesign
Semiconductor Pages: | 1,831 today → ~1,688 target (end-2026), EN + KO
Newsroom Pages: | EN 899 (news 250 / tags 650) + KO 10,034 (articles 3K / tags 7K)
Languages: | EN + KO (2 locales)
Dynamic Areas: | S.LSI Parts PD (PIM, 71) + product-security-updates (CVE, 197)
Date: | August 2026
Prepared by: | Adobe Professional Services
Version: | 1.0
CURRENT STATE — SEMICONDUCTOR SITE STRUCTURE (from internal analysis)
Lv.1 Area | Pages | Difficulty | Notes
Home | 1 | High
Product (incl. Memory 66, S.LSI 129, Parts PD 71) | 266 | High | Parts PD = PIM (dynamic)
Applications | 9 | High
Support (incl. tools-resources 129) | 376 | Low | Dictionary & Fabrication Process
→ product-security-updates (CVE) | 197 | - | Dynamic CVE pages
Technologies | 16
Foundry | 34
News & Event (News 266, Local 111, Events 114, Tech Blog 465) | 956 | Low
ESG (Sustainability 62, Accessibility 2, EHS 28) | 92 |  | Sustainability = redesign planned
About Us (About 41, SAS 15, SAIT 7, SSIR 3, SIRC 1) | 67 |  | About Us = redesign planned
TOTAL (Semiconductor, pre-reduction) | 1,831 |  | → ~1,688 target end-2026
SCOPE SUMMARY
Metric | Semiconductor Site | Newsroom (Incremental)
Source Platform | AEM On-Premise | WordPress
Pages | 1,688 (EN+KO) | EN 899 + KO 10,034
→ Articles / content pages | 1,688 | ~3,250
→ Generated tag/taxonomy pages | — | ~7,650 (template + index)
Languages | EN + KO | EN + KO
Target EDS Blocks | ~24 blocks | +5 (mostly reuse)
→ Reuse (style only) | 10 | 2-3
→ Extend / Custom | 14 | 2-3
Dynamic Integrations | PIM (Parts PD), CVE feed, Search | —
New UI/Components | Full design system | None (reuses site design)
Total Effort (Person-Days) | 426 | 126
Duration | ~5-6 months | +5-6 weeks (overlapping)
COMBINED TOTAL (base delivery) | 552 | person-days
+ PM/Coord (15%) + Contingency (10%) | 138 | PM 83 + Cont 55
GRAND TOTAL (Combined) | 690 | ~6-7 months, 6-7 FTEs
ARCHITECTURE: On-Premise / WordPress (AS-IS) vs. EDS SaaS (TO-BE)
★ Two platforms today (AEM on-prem + WordPress) → consolidated into ONE EDS site
★ AEM on-prem server-side rendering (HTL/Sling) → EDS client-side vanilla JS decoration
★ Self-managed infra, OS patching, upgrades → Adobe-managed cloud, continuous updates
★ Dispatcher/CDN tuning → Edge CDN by default; 100/100 Lighthouse achievable
★ Dynamic areas (Parts PD / PIM, CVE) must be RE-INTEGRATED via EDS blocks + APIs
★ WordPress articles/tags → document/content-source authoring + query-index for taxonomy
★ AEM components → re-implemented as EDS blocks (no auto-migration between architectures)
★ Ongoing subscription (SaaS) vs. capitalized on-prem infra — lower TCO, faster time-to-market
NOTE: Tag/taxonomy pages (~7,650) are generated by a template + query index, not migrated per-page.
Estimate is planning-grade (±15-20%); firm-up recommended after a Discovery spike on PIM & CVE integrations.

## Semiconductor Site
Samsung Semiconductor Site — EDS Migration (semiconductor.samsung.com)
Source: AEM On-Premise ¦ EN + KO ¦ 1,831 pages to ~1,688 target ¦ Dynamic: Parts PD (PIM), CVE (197)
# | Work Stream | Task | Complexity | Effort (Days) | Resources | Notes
DISCOVERY & ARCHITECTURE
1.1 |  | Site audit — 1,831 to 1,688 pages, EN+KO, 8 areas | High | 8 | 1 Arch + 1 Dev | Map content tree; reconcile deletions (consumer-storage, customer-service)
1.2 |  | Component & template mapping (AEM to EDS blocks) | High | 8 | 1 Architect | Consolidate AEM components into ~30-35 EDS blocks
1.3 |  | Integration architecture (Parts PD/PIM, CVE, Search) | High | 8 | 1 Arch + 1 Dev | Externalization strategy for dynamic areas
1.4 |  | Design system extraction | Medium | 5 | 1 Designer | Tokens, typography, spacing from source
1.5 |  | Migration strategy & phasing document | Medium | 4 | 1 PM | IA sign-off, area-by-area cutover plan
|  | Subtotal - Discovery |  | 33
FOUNDATION & SETUP
2.1 |  | EDS project scaffolding, CI/CD, environments | Low | 3 | 1 Dev | Repo, AEM Code Sync, preview/live
2.2 |  | Global styles & design tokens | High | 10 | 1 Dev | Design system from extracted tokens
2.3 |  | Header / multi-level mega-menu (EN/KO) | High | 12 | 1 Dev | 8 Lv.1 areas, responsive, language switch
2.4 |  | Footer block (legal, social, regional) | Medium | 5 | 1 Dev | Multi-column, EN/KO variants
2.5 |  | Core page templates (Home/Product/Support/Article/Static) | High | 12 | 1 Dev | Document-based authoring templates
2.6 |  | i18n framework (EN/KO) | Medium | 6 | 1 Dev | en.json, ko.json, locale routing
2.7 |  | Search infrastructure (EN/KO) | High | 8 | 1 Dev | Replace AEM search; index setup
|  | Subtotal - Foundation |  | 56
BLOCK DEVELOPMENT — REUSE (Block Library to brand CSS only)
3.1 |  | Hero block | Low | 3 | 1 Dev | REUSE: home/product/section heroes
3.2 |  | Cards block (feature/product) | Low | 3 | 1 Dev | REUSE: card variants
3.3 |  | Carousel block | Low | 3 | 1 Dev | REUSE: content/product carousel
3.4 |  | Accordion block | Low | 2 | 1 Dev | REUSE: FAQ, expandable
3.5 |  | Tabs block | Low | 2 | 1 Dev | REUSE: content switching
3.6 |  | Table block | Low | 2 | 1 Dev | REUSE: responsive data tables
3.7 |  | Breadcrumb block | Low | 1 | 1 Dev | REUSE: auto-generated from nav
3.8 |  | CTA / banner block | Low | 2 | 1 Dev | REUSE: call-to-action
3.9 |  | Columns / grid block | Low | 2 | 1 Dev | REUSE: layout grids
3.10 |  | Video embed block | Low | 2 | 1 Dev | REUSE: YouTube/custom player
|  | Subtotal - Reuse Blocks (10 blocks) |  | 22 | Avg 2.2 days/block (brand CSS only)
BLOCK DEVELOPMENT — EXTEND (Library + customization)
3.11 |  | Contact form block (contact-info) | High | 8 | 1 Dev | EXTEND: multi-step, validation, EN/KO
3.12 |  | Article grid block (News / Local News) | Medium | 6 | 1 Dev | EXTEND: filters, pagination, sorting
3.13 |  | Event listing / calendar block (Events) | High | 6 | 1 Dev | EXTEND: event filtering, calendar view
3.14 |  | Download / resources block (tools-resources) | Medium | 5 | 1 Dev | EXTEND: Dictionary & Fabrication files
3.15 |  | Quality / regulatory document block | Medium | 5 | 1 Dev | EXTEND: quality-mgmt, disclosure-policy
3.16 |  | Related resources block | Medium | 4 | 1 Dev | EXTEND: dynamic recommendations
3.17 |  | LNB / local navigation block | Medium | 4 | 1 Dev | EXTEND: product section nav
|  | Subtotal - Extend Blocks (7 blocks) |  | 38 | Avg 5.4 days/block
BLOCK DEVELOPMENT — CUSTOM (full build)
3.18 |  | Product spec block | High | 10 | 1 Dev | CUSTOM: dynamic spec tables, comparison
3.19 |  | Product finder block | High | 12 | 1 Dev | CUSTOM: filterable catalog (Memory, S.LSI)
3.20 |  | S.LSI Parts PD block (PIM-driven) | High | 12 | 1 Dev | CUSTOM: dynamic product data (71 pages)
3.21 |  | CVE / product-security-updates block | High | 12 | 1 Dev | CUSTOM: dynamic security feed (197 pages)
3.22 |  | Tech Blog article block | Medium | 6 | 1 Dev | CUSTOM: 465-page blog template
3.23 |  | Foundry / Technologies showcase block | Medium | 5 | 1 Dev | CUSTOM: process technology display
3.24 |  | Applications showcase block | Medium | 5 | 1 Dev | CUSTOM: application cards
|  | Subtotal - Custom Blocks (7 blocks) |  | 62 | Avg 8.9 days/block
INTEGRATIONS & DYNAMIC SERVICES
4.1 |  | PIM / S.LSI Parts PD API integration | High | 15 | 1 Backend Dev | Dynamic product data service (71 pages)
4.2 |  | CVE / product-security-updates feed | High | 15 | 1 Backend Dev | Dynamic security advisory feed (197 pages)
4.3 |  | Search integration (EN/KO) | High | 10 | 1 Dev | Indexing, suggestions across site
4.4 |  | Form submission backend (contact-info) | Medium | 5 | 1 Dev | API endpoints, notifications
4.5 |  | Analytics & tag management setup | Medium | 5 | 1 Dev | Data layer, event tracking
|  | Subtotal - Integrations |  | 50
CONTENT & ASSET MIGRATION (1,688 pages, EN+KO)
5.1 |  | Import script development (parsers/transformers) | High | 15 | 1 Dev | Template-aware importer per page type
5.2 |  | Asset migration & optimization (WebP/AVIF) | Medium | 8 | 1 Dev | Product images, media, documents
5.3 |  | Content migration — Product (471) + Applications (9) | High | 14 | 1 Dev + 1 Content | Product 266, Memory 66, S.LSI 129
5.4 |  | Content migration — Support (376) | High | 12 | 1 Dev + 1 Content | Incl. tools-resources, quality (excl. CVE dynamic)
5.5 |  | Content migration — News & Event (956) | Medium | 16 | 1 Dev + 1 Content | News 266, Local 111, Events 114, Tech Blog 465
5.6 |  | Content migration — ESG (92) + About Us (67) | Medium | 8 | 1 Content | Sustainability & About Us = redesign planned
5.7 |  | Content migration — Technologies (16) + Foundry (34) | Low | 3 | 1 Content | Standard pages
5.8 |  | URL redirect mapping (1,688 URLs, EN/KO) | High | 8 | 1 Dev | Bulk 301s, SEO preservation
5.9 |  | Metadata & SEO migration | Medium | 6 | 1 Dev | Schema, OG tags, sitemap
|  | Subtotal - Content & Asset Migration |  | 90 | 1,688 pages EN+KO
TESTING & QUALITY ASSURANCE (EN/KO)
6.1 |  | Performance testing & optimization | High | 8 | 1 Dev | Lighthouse 100 target, Core Web Vitals
6.2 |  | Accessibility testing (WCAG 2.1 AA) | High | 8 | 1 QA | All blocks, EN/KO
6.3 |  | Cross-browser / device testing | Medium | 6 | 1 QA | Chrome, Safari, Firefox, Edge, mobile
6.4 |  | Content QA (EN/KO, area-by-area) | High | 14 | 1-2 QA | Visual regression, links, media
6.5 |  | SEO validation (1,688 URLs) | Medium | 5 | 1 Dev | Redirect + crawl test
6.6 |  | Integration testing (PIM, CVE, Search) | High | 6 | 1 Dev | End-to-end validation
|  | Subtotal - Testing & QA |  | 47
LAUNCH & HANDOVER
7.1 |  | Go-live planning & staged cutover | High | 6 | 1 PM + 1 Dev | DNS, redirects, publishing
7.2 |  | Author training & documentation (EN/KO) | Medium | 6 | 1 PM | EDS authoring guides
7.3 |  | Developer handover | Medium | 4 | 1 Dev | Code, architecture, API docs
7.4 |  | Post-launch hypercare (2-3 weeks) | High | 12 | 1 Dev + 1 QA | Monitoring, hotfixes
|  | Subtotal - Launch & Handover |  | 28
| GRAND TOTAL — SEMICONDUCTOR SITE |  |  | 426 |  | ~5-6 months with 4-5 FTEs

## Newsroom
Samsung Semiconductor Newsroom — Incremental Effort (news.samsungsemiconductor.com)
Source: WordPress ¦ EN 899 + KO 10,034 ¦ Article-centric ¦ Shares site design/foundation
# | Work Stream | Task | Complexity | Effort (Days) | Resources | Notes
DISCOVERY (INCREMENTAL)
N1.1 |  | Newsroom audit & inventory (WP export) | Medium | 5 | 1 Architect | EN 899 + KO 10,034; article/category/tag
N1.2 |  | Content-type mapping (article/category/tag) | Medium | 3 | 1 Architect | Map WP types to EDS model
N1.3 |  | Taxonomy / tag strategy (~7,650 tag pages) | Medium | 3 | 1 Architect | Tags generated via template + query index
|  | Subtotal - Discovery |  | 11
TEMPLATES & BLOCKS (INCREMENTAL — article-centric)
N2.1 |  | News article template | Medium | 6 | 1 Dev | Article body, hero, author, share
N2.2 |  | Category / listing template | Medium | 5 | 1 Dev | Paginated article listing
N2.3 |  | Tag / taxonomy template (generated) | Medium | 5 | 1 Dev | Query-index driven; not per-page authored
N2.4 |  | Article grid / related / popular block | Low | 4 | 1 Dev | REUSE from Semiconductor site
N2.5 |  | Author / date / share metadata block | Low | 3 | 1 Dev | Byline, publish date, social share
|  | Subtotal - Templates & Blocks |  | 23 | No new UI/components (reuses site design)
CONTENT MIGRATION (WordPress to EDS)
N3.1 |  | WP to EDS import pipeline (REST/export mapping) | High | 12 | 1 Dev | WordPress API/export parser
N3.2 |  | EN articles migration (250) | Medium | 8 | 1 Dev + 1 Content | News + article content
N3.3 |  | KO articles migration (3,000) | High | 30 | 1 Dev + 2 Content | Largest volume; automated + QA
N3.4 |  | Tag / taxonomy generation (~7,650 EN+KO) | Medium | 10 | 1 Dev | Generated, NOT per-page authored
N3.5 |  | Media / asset migration (WP uploads) | Medium | 8 | 1 Dev | Images, featured media
N3.6 |  | URL redirects (news.samsungsemiconductor.com) | Medium | 6 | 1 Dev | 301 map, SEO preservation
|  | Subtotal - Content Migration |  | 74 | ~3,250 articles + ~7,650 generated tags
TESTING & LAUNCH (INCREMENTAL)
N4.1 |  | Newsroom content QA (EN/KO sampling) | Medium | 8 | 1 QA | Visual regression, links
N4.2 |  | Performance & SEO (news pages) | Medium | 5 | 1 Dev | Lighthouse, crawl, redirects
N4.3 |  | Go-live & hypercare (newsroom) | Medium | 5 | 1 Dev + 1 QA | Cutover + monitoring
|  | Subtotal - Testing & Launch |  | 18
| GRAND TOTAL — NEWSROOM (INCREMENTAL) |  |  | 126 |  | ~5-6 additional weeks

## Combined Summary
Migration Effort Summary — DS CMS Consolidation
Semiconductor Site + Newsroom → AEM Edge Delivery Services (SaaS)
Work Stream | Semi Site (Days) | Newsroom Incr. (Days) | Combined (Days) | Combined (Weeks)
Discovery & Architecture | 33 | 11 | 44 | 2.0
Foundation & Setup | 56 | — | 56 | 2.5
Block Dev — Reuse | 22 | 23 | 45 | 2.0
Block Dev — Extend | 38 | — | 38 | 1.7
Block Dev — Custom | 62 | — | 62 | 2.8
Integrations & Dynamic Services (PIM/CVE/Search) | 50 | — | 50 | 2.3
Content & Asset Migration | 90 | 74 | 164 | 7.5
Testing & QA | 47 | 18 | 65 | 3.0
Launch & Handover | 28 | — | 28 | 1.3
TOTAL — Semiconductor Site | 426 | — | 426 | ~5-6 months
TOTAL — Newsroom Incremental | — | 126 | 126 | ~5-6 weeks
BASE DELIVERY (Combined) | 426 | 126 | 552 | ~25 wks
+ PM & Coordination (15%) |  |  | 83
+ Contingency / Risk (10%) |  |  | 55
GRAND TOTAL — COMBINED (Semi + Newsroom) |  |  | 690 | ~6-7 months
KEY ASSUMPTIONS
• Both EN + KO in scope for both sites.
• Newsroom ~7,650 tag/taxonomy pages are template-generated (not per-page migration).
• Automation-first migration: reusable import pipelines per template + per-page QA.
• Design extracted from existing sites; Sustainability & About Us redesigns treated as build.
• Dynamic areas (PIM Parts PD, CVE) require integration, not lift-and-shift.
• Excludes flagged pages: consumer-storage (38, delete), customer-service (1, delete), collaboration-hub (1, undecided).
• Estimate covers build + migrate + launch + 2-3 week hypercare; ongoing BAU excluded.

## Risk Register
Risk Register — DS CMS Migration
ID |  | Risk Description | Likelihood | Impact | Mitigation Strategy | Owner
| R1 | PIM / S.LSI Parts PD integration underspecified (71 pages) | High | High | Discovery spike + POC in Phase 0/3; API contract early | Architect
| R2 | CVE / product-security-updates dynamic feed (197 pages) | High | High | Define feed source & schema early; build as dedicated block | Backend Dev
| R3 | Sustainability & About Us redesign (개편 예정) not finalized | High | Medium | Lock designs before Phase 2; treat as design dependency | PM
| R4 | Newsroom KO volume (10,034 incl. tags) | Confirmed | High | Tags generated (not per-page); strong article automation | Content Eng
| R5 | WordPress → EDS content-type mapping (article/category/tag) | High | Medium | Build robust import pipeline; validate mapping on sample | Dev
| R6 | Two-platform consolidation into single IA | Confirmed | High | IA workshop; reconcile navigation & taxonomy upfront | Architect
| R7 | EN/KO content parity gaps | Medium | Medium | Reconcile inventory in Discovery; per-locale QA | Content Eng
| R8 | Flagged/undecided pages (consumer-storage, collaboration-hub) | Confirmed | Low | Excluded from base; add on client decision | PM
| R9 | SEO ranking impact — bulk URL redirects (two domains) | High | High | Comprehensive redirect map; staged rollout; 90-day monitor | SEO
| R10 | AEM components → EDS block re-implementation | Medium | Medium | POC key blocks in Phase 1; validate mapping assumptions | Architect
| R11 | Content freeze / SME availability for UAT & approvals | Medium | Medium | Agree content-freeze window & UAT SLAs upfront | PM
| R12 | Search re-platforming (replace AEM search, EN/KO) | Medium | Medium | Select search provider early; index during migration | Dev

## Resource Plan
Recommended Team Structure (Combined Semi + Newsroom)
Role | Count | Responsibilities | Duration
Solution Architect | 1 | Component/template mapping, integration architecture, IA consolidation | Full duration
Senior EDS Developer | 2 | Block development (extend/custom), EDS patterns, performance | Full duration
Backend Developer | 1 | PIM/Parts PD API, CVE feed, search integration | Months 2-5
Frontend Developer | 1 | Block styling (reuse tier), CSS, responsive, a11y | Months 2-6
Content / Migration Engineer | 2 | Import pipelines, 1,688 site pages + 3,250 articles, per-locale QA | Months 2-7
QA Engineer | 1 | EN/KO testing, accessibility, cross-browser, integration tests | Months 3-7
Project Manager | 0.5 | Cutover planning, stakeholder coordination, training | Full duration
UX Designer | 0.5 | Design system extraction; Sustainability & About Us redesign | Months 1-3
Total Team: 6-7 FTEs at peak (months 3-6)
Ramp: Start with 4, scale to 7 at month 3, taper to 3 for hypercare

## Timeline
Project Timeline — DS CMS Combined Migration
~6-7 months ¦ Two-site consolidation, staged cutover
| M1 | M2 | M3 | M4 | M5 | M6 | M7
Phase 1: Discovery & Architecture
Phase 2: Foundation & Setup
Phase 3a: Block Reuse (style only)
Phase 3b: Block Extend (customize)
Phase 3c: Block Custom (Semi)
Phase 4: Integrations (PIM/CVE/Search)
Phase 5: Content Migration — Semi Site
Phase 6: Newsroom Templates & Migration
Phase 7: Testing & QA (EN/KO)
Phase 8: UAT & Launch (staged cutover)
Phase 9: Hypercare (2-3 weeks)
Consolidation Strategy
• Two sites merged into one EDS site; single IA and navigation.
• Semiconductor site foundation & blocks built first; Newsroom reuses design.
• Dynamic integrations (PIM Parts PD, CVE) run in parallel on critical path.
• Staged cutover: low-risk areas → high-traffic Product/Support → Newsroom → global launch.