## Executive Summary
ADOBE EXPERIENCE MANAGER
Edge Delivery Services Migration Estimate
Samsung Semiconductor & LED Division
REVISED v3.0 — Based on Samsung Internal Migration Analysis + DAM Report
PROJECT OVERVIEW
Client: | Samsung Electronics - Semiconductor Division
Source Platform: | AEM 6.5 On-Premise (Large instance)
Target Platform: | AEM Edge Delivery Services (Cloud)
Websites in Scope: | semiconductor.samsung.com + led.samsung.com
Total Pages: | 31,603 pages across 9 regions
Total Components: | 643 component nodes / 132+ types
DAM Size: | 229.17 GB ¦ 1,692,306 nodes ¦ 8,815,757 properties
Languages: | 4 locales (EN, KR, JP, CN) × 9 regions
Samsung Classification: | LARGE (9-12 months standard)
Date: | May 2026
Prepared by: | Adobe Professional Services
Version: | 3.0 (Based on Samsung internal analysis document)
CURRENT STATE — FROM SAMSUNG INTERNAL ANALYSIS
Region | Size | Pages | Notes
global | 347 MB | 7,128 | Global master + multi-region master content
kr | 225 MB | 5,674 | Korea (ko_kr)
us | 193 MB | 5,351 | US + careers dedicated components
emea | 171 MB | 5,041 | Europe + searchjobs dedicated
jp | 171 MB | 4,007 | Japan (ja_jp)
cn | 155 MB | 4,298 | China (zh_cn)
de | 2.2 MB | 33 | Germany (small, insights/newsroom only)
ssir | 936 KB | 19 | SSIR dedicated small site
ds-test | 6.2 MB | 52 | Test/staging content
TOTAL | 1.3 GB | 31,603
COMPONENT INVENTORY SUMMARY
Category | Types | Key Components
global/content/statics | 44 | hero, accordion, carousel, feature-benefit, table, etc.
global/content/common | 26 | gnb, footer, breadcrumb, hashtag, contactus, cookie
global/content/product | 21 | hero, lnb, spec, product-finder, related-resources
global/content/event | 16 | login, mypage, webinar-regist, subscription
global/content/article | 11 | article-grid, event-calendar, event-grid, popular-news
global/content/search | 4 | search-grid, search-publications
global/content/careers | 2 | job-list, job-detail
global/page (templates) | 6 | product-page, content-page, empty-page, etc.
Region-specific | 2 | emea/searchjobs, us/careers
TOTAL | 132+ types / 643 nodes | Including variants
SCOPE SUMMARY (REVISED v3.0)
Metric | Semiconductor Only | Semiconductor + LED
Total Pages (confirmed) | 31,603 | 31,603 + ~80 LED pages
Regions | 9 | 9 + 6 LED regional variants
Languages/Locales | 4 (EN, KR, JP, CN) | 4
Source Components (AEM) | 643 nodes / 132+ types | 643 + LED-specific
Target EDS Blocks | 35-40 | 45-52
→ Reuse from Block Library | 12-15 (style only) | 15-18
→ Extend/Customize | 10-12 | 12-15
→ Custom Development | 10-13 | 15-19
WCM Templates → EDS Templates | 44 + 6 types → 8-10 EDS | 8-10 + 3 LED
OSGi Bundles to Externalize | 6 custom + 3 third-party | Same (shared)
External Integrations | MySQL, Akamai, Search | MySQL, Akamai, Search + LED tools
Custom Admin UIs | 5 (PIM, privacy, terms, site-ia, tasks) | Same (shared)
DAM Assets | 229 GB / 1.69M nodes | 229 GB / 1.69M nodes
Total Effort (Person-Days) | 680-780 | 830-950
Duration | 9-12 months | 11-14 months
CRITICAL ARCHITECTURE DIFFERENCES: AEM On-Prem vs EDS
★ AEM 6.5 uses server-side rendering (HTL/Sling) — EDS uses client-side vanilla JS decoration
★ 643 AEM components (HTL) CANNOT be auto-migrated to EDS blocks — must be re-implemented
★ 6 OSGi bundles (Java) have NO equivalent in EDS — must be externalized as API microservices
★ MySQL direct JDBC connection NOT possible in EDS — requires REST API service layer
★ Akamai NetStorage dependency → EDS has its own CDN; assets delivered from edge
★ 5 Custom Admin UIs (PIM, privacy, etc.) → requires separate headless admin application
★ 44 WCM Templates → reduced to 8-10 EDS page templates (document-based authoring)
★ Content migration: 31,603 pages require automated import with per-region validation
NOTE: AEM Modernization Tools/Agent are designed for AEM 6.x → AEMaaCS (same architecture).
They do NOT apply to EDS migration since EDS is architecturally different (no JCR, no OSGi, no HTL).

## Semiconductor - Detailed
Samsung Semiconductor - EDS Migration (REVISED v3.0)
Based on: 31,603 pages ¦ 643 components ¦ 229GB DAM ¦ 9 regions ¦ 6 OSGi bundles
# | Work Stream | Task | Complexity | Effort (Days) | Resources | Notes
DISCOVERY & ARCHITECTURE
1.1 |  | Site Audit — 31,603 pages across 9 regions | High | 12 | 1 Arch + 1 Dev | Crawl all regions, map content trees
1.2 |  | DAM Audit — 229GB / 1.69M nodes classification | High | 10 | 1 Arch + 1 Dev | Active vs archive, duplicate detection
1.3 |  | Component Mapping (643 → EDS blocks) | High | 12 | 1 Architect | Map 132+ component types to 35-40 EDS blocks
1.4 |  | Template Mapping (44 WCM + 6 types → 8-10 EDS) | High | 6 | 1 Architect | Simplify 50 templates to EDS model
1.5 |  | Integration Architecture (MySQL, Akamai, APIs) | High | 10 | 1 Arch + 1 Dev | Externalization strategy for JDBC, NetStorage
1.6 |  | Admin UI Externalization Strategy (5 UIs) | High | 6 | 1 Architect | PIM, privacy, terms, site-ia, taskmanagement
1.7 |  | Design System Extraction | Medium | 5 | 1 Designer | Tokens, typography, spacing from 254 CSS files
1.8 |  | Migration Strategy & Phasing Document | Medium | 5 | 1 PM | Region-by-region cutover plan
|  | Subtotal - Discovery |  | 66
FOUNDATION & SETUP
2.1 |  | EDS Project Scaffolding | Low | 3 | 1 Dev | Repo setup, CI/CD, environments
2.2 |  | Global Styles & Design Tokens (from 254 CSS files) | High | 12 | 1 Dev | Extract from 582 JS / 254 CSS, create design system
2.3 |  | Header/Navigation Block (cm-semi-gnb) | High | 12 | 1 Dev | Mega menu, 9 regions, responsive
2.4 |  | Footer Block (from cm-semi-gnb footer) | Medium | 5 | 1 Dev | Multi-column, social, legal, regional variants
2.5 |  | Core Page Templates (8-10 from 44+6 WCM) | High | 15 | 1 Dev | Product, content, article, event, static, marketing
2.6 |  | i18n Framework (4 locales × 9 regions) | High | 12 | 1 Dev | en.json, ko_kr.json, ja_jp.json, zh_cn.json
2.7 |  | Search Infrastructure (from sr-semi-search-*) | High | 10 | 1 Dev | Search grid, publications, suggestions
2.8 |  | Authentication/Login Framework (ev-semi-login) | High | 8 | 1 Dev | User login, mypage, event registration
|  | Subtotal - Foundation |  | 77
BLOCK DEVELOPMENT — REUSE (AEM Block Library → brand CSS only)
3.1 |  | Hero Block (from st-semi-hero, pd-semi-hero) | Low | 3 | 1 Dev | REUSE: 2 source components → 1 block + variants
3.2 |  | Cards Block (multiple variants) | Low | 3 | 1 Dev | REUSE: Feature cards, product cards
3.3 |  | Carousel Block (from st-semi carousel) | Low | 3 | 1 Dev | REUSE: Content carousel, product carousel
3.4 |  | Accordion Block (from st-semi accordion) | Low | 2 | 1 Dev | REUSE: FAQ, expandable sections
3.5 |  | Tabs Block | Low | 2 | 1 Dev | REUSE: Content switching tabs
3.6 |  | Video Embed Block | Low | 2 | 1 Dev | REUSE: YouTube/custom player
3.7 |  | Table Block (from st-semi table) | Low | 2 | 1 Dev | REUSE: Data tables, responsive
3.8 |  | Breadcrumb Block (from cm-semi breadcrumb) | Low | 1 | 1 Dev | REUSE: Auto-generated from nav
3.9 |  | CTA Block | Low | 2 | 1 Dev | REUSE: Call-to-action banners
3.10 |  | Columns/Grid Block | Low | 2 | 1 Dev | REUSE: Layout grids
3.11 |  | Image Gallery Block | Low | 2 | 1 Dev | REUSE: Lightbox, grid layout
3.12 |  | Feature-Benefit Block (from st-semi feature-benefit) | Low | 3 | 1 Dev | REUSE: Product features display
|  | Subtotal - Reuse Blocks (12 blocks) |  | 27 |  | Avg 2.3 days/block (brand CSS only)
BLOCK DEVELOPMENT — EXTEND (Library + significant customization)
3.13 |  | Contact Form Block (from cm-semi contactus) | High | 10 | 1 Dev | EXTEND: Multi-step, regional variants, validation
3.14 |  | Article Grid Block (from ar-semi-article-grid) | Medium | 6 | 1 Dev | EXTEND: Filters, pagination, sorting
3.15 |  | Event Calendar Block (from ar-semi event-calendar) | High | 8 | 1 Dev | EXTEND: Calendar view, event filtering
3.16 |  | Popular News Block (from ar-semi popular-news) | Medium | 5 | 1 Dev | EXTEND: Dynamic content, trending
3.17 |  | Download/Resources Block | Medium | 5 | 1 Dev | EXTEND: File downloads with filters
3.18 |  | Cookie/Privacy Block (from cm-semi cookie) | Medium | 6 | 1 Dev | EXTEND: OneTrust + Samsung privacy policy
3.19 |  | Hashtag/Tag Filter Block (from cm-semi hashtag) | Medium | 5 | 1 Dev | EXTEND: Content tagging/filtering
3.20 |  | Related Resources Block (from pd-semi related-resources) | Medium | 5 | 1 Dev | EXTEND: Dynamic content recommendations
3.21 |  | Subscription Block (from ev-semi subscription) | Medium | 5 | 1 Dev | EXTEND: Newsletter, event signup
3.22 |  | LNB Block (from pd-semi-lnb) | Medium | 4 | 1 Dev | EXTEND: Local navigation bar for products
|  | Subtotal - Extend Blocks (10 blocks) |  | 59 |  | Avg 5.9 days/block
BLOCK DEVELOPMENT — CUSTOM (No library equivalent, full build)
3.23 |  | Product Spec Block (from pd-semi-spec) | High | 12 | 1 Dev | CUSTOM: Dynamic spec tables, comparison
3.24 |  | Product Finder Block (from pd-semi product-finder) | High | 15 | 1 Dev | CUSTOM: Filterable product catalog, interactive
3.25 |  | Job List/Detail Block (from cr-semi-job-*) | High | 10 | 1 Dev | CUSTOM: Careers integration, search, apply
3.26 |  | Webinar Registration Block (from ev-semi webinar-regist) | High | 8 | 1 Dev | CUSTOM: Registration flow, calendar integration
3.27 |  | Event Grid Block (from ar-semi event-grid) | Medium | 6 | 1 Dev | CUSTOM: Events display with filters
3.28 |  | Search Publications Block (from sr-semi search-publications) | Medium | 6 | 1 Dev | CUSTOM: Document/whitepaper search
3.29 |  | MyPage Block (from ev-semi-mypage) | High | 10 | 1 Dev | CUSTOM: User dashboard, event history
3.30 |  | Searchjobs Block (from emea/searchjobs) | Medium | 6 | 1 Dev | CUSTOM: Regional job search
3.31 |  | Regional Contact Tabs Block | Medium | 5 | 1 Dev | CUSTOM: Region-based content switching
3.32 |  | Foundry Services Block | Medium | 5 | 1 Dev | CUSTOM: Process technology showcase
3.33 |  | Application Showcase Block | Medium | 5 | 1 Dev | CUSTOM: AI, Server, Auto, Network cards
|  | Subtotal - Custom Blocks (11 blocks) |  | 88 |  | Avg 8 days/block
|  | TOTAL BLOCK DEVELOPMENT (33 blocks from 643 components) |  | 174 |  | 643 components consolidated into 33 EDS blocks
EXTERNAL SERVICES & API LAYER (OSGi bundle replacement)
4.1 |  | MySQL REST API Service (replace JDBC connector) | High | 20 | 1 Backend Dev | ★ semi-apiservice externalization, REST endpoints
4.2 |  | Akamai/CDN Migration (replace NetStorageKit) | High | 10 | 1 DevOps | ★ Cloud Manager CDN or direct EDS delivery
4.3 |  | semi-common bundle functions → Edge/Serverless | High | 15 | 1 Dev | ★ 1.7MB core bundle → serverless functions
4.4 |  | semi-product API endpoints | Medium | 8 | 1 Dev | Product data services
4.5 |  | semi-article API endpoints | Medium | 6 | 1 Dev | Article/content services
4.6 |  | semi-gnb API endpoints (menu data) | Medium | 5 | 1 Dev | Navigation data service
4.7 |  | PIM Admin UI (external SPA/headless) | High | 15 | 1 Dev | ★ Product info management app
4.8 |  | Privacy/Terms Admin UI (external) | Medium | 8 | 1 Dev | Consent & policy management
4.9 |  | Site-IA & Task Management Admin (external) | Medium | 8 | 1 Dev | IA management + task workflow
|  | Subtotal - External Services |  | 95 |  | Replaces 6 OSGi bundles + 5 admin UIs
CONTENT & ASSET MIGRATION (31,603 pages + 229GB DAM)
5.1 |  | Import Script Development (multi-region) | High | 15 | 1 Dev | Region-aware importer for 9 regions
5.2 |  | DAM Audit & Cleanup (229GB) | High | 12 | 1 Dev + 1 Content | Classify 1.69M nodes, remove duplicates/archive
5.3 |  | DAM Migration Phase 1 — Critical assets (~60GB) | High | 15 | 1 Dev | Product images, heroes, logos, active media
5.4 |  | DAM Migration Phase 2 — Supporting assets (~80GB) | Medium | 12 | 1 Dev | Blog images, event media, documents
5.5 |  | Asset Optimization & Format Conversion | Medium | 8 | 1 Dev | WebP/AVIF conversion, compression, CDN setup
5.6 |  | Content Migration — global region (7,128 pages) | High | 20 | 1 Dev + 2 Content | Master content + validation
5.7 |  | Content Migration — kr region (5,674 pages) | High | 15 | 1 Dev + 1 Content | Korean locale content
5.8 |  | Content Migration — us region (5,351 pages) | High | 15 | 1 Dev + 1 Content | US content + careers
5.9 |  | Content Migration — emea region (5,041 pages) | High | 14 | 1 Dev + 1 Content | European content + searchjobs
5.10 |  | Content Migration — jp region (4,007 pages) | Medium | 12 | 1 Dev + 1 Content | Japanese locale
5.11 |  | Content Migration — cn region (4,298 pages) | Medium | 12 | 1 Dev + 1 Content | Chinese locale
5.12 |  | Content Migration — de/ssir/ds-test (104 pages) | Low | 3 | 1 Content | Small regions
5.13 |  | URL Redirect Mapping (31,603 URLs) | High | 12 | 1 Dev | Bulk 301 redirects, SEO preservation
5.14 |  | Metadata & SEO Migration | Medium | 8 | 1 Dev | Schema, OG tags, sitemap for all regions
|  | Subtotal - Content & Asset Migration |  | 173 |  | 31,603 pages + 229GB assets
INTEGRATIONS
6.1 |  | Search Integration (replace sr-semi-search-*) | High | 12 | 1 Dev | Algolia/Coveo indexing for 31K pages
6.2 |  | Analytics Setup (Adobe Analytics) | Medium | 8 | 1 Dev | Event tracking, data layer, 9 regions
6.3 |  | Form Submission Backend | Medium | 5 | 1 Dev | API endpoints, notifications
6.4 |  | CDN & Edge Configuration | Medium | 5 | 1 DevOps | Caching, headers, security, replace Akamai
6.5 |  | Event/Webinar Platform Integration | Medium | 6 | 1 Dev | Registration, calendar sync
|  | Subtotal - Integrations |  | 36
TESTING & QUALITY ASSURANCE (9 regions × 4 locales)
7.1 |  | Performance Testing & Optimization | High | 10 | 1 Dev | Lighthouse 95+, Core Web Vitals all templates
7.2 |  | Accessibility Testing (WCAG 2.1 AA) | High | 10 | 1 QA | All 33 blocks × accessibility
7.3 |  | Cross-browser/Device Testing | Medium | 8 | 1 QA | Chrome, Safari, Firefox, Edge, mobile
7.4 |  | Content QA — Region-by-region (9 regions) | High | 25 | 2 QA | Visual regression, links, media per region
7.5 |  | Asset Integrity Verification | Medium | 6 | 1 QA | Verify migrated DAM assets render correctly
7.6 |  | SEO Validation (31K URLs) | High | 8 | 1 Dev | Rankings preservation, crawl test, redirects
7.7 |  | Security Testing | Medium | 5 | 1 DevOps | Headers, CSP, vulnerability scan
7.8 |  | Integration Testing (MySQL API, Search, Events) | High | 8 | 1 Dev | End-to-end integration validation
7.9 |  | UAT Support (region-by-region cutover) | High | 15 | 1 Dev + 1 QA | Staged: ssir/de → kr/jp → cn → us/emea → global
|  | Subtotal - Testing & QA |  | 95 |  | 9 regions × 4 locales matrix
LAUNCH & HANDOVER
8.1 |  | Go-Live Planning — Staged Regional Cutover | High | 8 | 1 PM + 1 Dev | ssir/de → kr/jp → cn → us/emea → global
8.2 |  | Author Training & Documentation | Medium | 8 | 1 PM | EDS authoring guides for 4 locale teams
8.3 |  | Developer Handover | Medium | 5 | 1 Dev | Code docs, architecture, API docs
8.4 |  | Post-Launch Hypercare (4 weeks - staged) | High | 20 | 1 Dev + 1 QA | Region-by-region monitoring, hotfixes
|  | Subtotal - Launch & Handover |  | 41
| GRAND TOTAL — SEMICONDUCTOR ONLY (REVISED v3.0) |  |  | 757 |  | ~9-11 months with 5-7 FTEs

## LED Website - Detailed
Samsung LED Website - Incremental Effort (REVISED v3.0)
Incremental when combined with Semiconductor ¦ Shares OSGi/Admin/DAM infrastructure
# | Work Stream | Task | Complexity | Effort (Days) | Resources | Notes
DISCOVERY (INCREMENTAL)
L1.1 |  | LED Site Audit & Inventory (~80 pages) | Medium | 5 | 1 Architect | Product catalog, 6 regions
L1.2 |  | LED Template & Block Mapping | Medium | 3 | 1 Architect | 3 additional templates
L1.3 |  | LED Navigation & IA Design | Medium | 3 | 1 Architect | Separate nav structure
|  | Subtotal - Discovery |  | 11
LED BLOCKS — REUSE (Style Only)
L2.1 |  | LED Product Category Block (reuse Cards) | Low | 3 | 1 Dev | REUSE: Mid/High/CSP/COB/Module cards
L2.2 |  | LED Application Gallery (reuse Gallery) | Low | 2 | 1 Dev | REUSE: Horticulture, automotive
L2.3 |  | Quick Downloads Block (reuse Resources) | Low | 2 | 1 Dev | REUSE: Datasheet repository
|  | Subtotal - LED Reuse Blocks |  | 7
LED BLOCKS — EXTEND
L2.4 |  | LED Spec Comparison Block | Medium | 6 | 1 Dev | EXTEND: Multi-product comparison table
L2.5 |  | Automotive LED Showcase | Medium | 4 | 1 Dev | EXTEND: Application-specific display
L2.6 |  | In-branding Program Block | Low | 3 | 1 Dev | EXTEND: Partner program info
L2.7 |  | Sales Network Block | Medium | 4 | 1 Dev | EXTEND: Regional sales contacts
|  | Subtotal - LED Extend Blocks |  | 17
LED BLOCKS — CUSTOM
L2.8 |  | LED Component Calculator | High | 12 | 1 Dev | CUSTOM: Interactive design calculator
L2.9 |  | LED Engine Calculator | High | 10 | 1 Dev | CUSTOM: Performance modeling tool
L2.10 |  | LED Module Configurator | High | 8 | 1 Dev | CUSTOM: Product selection wizard
L2.11 |  | Virtual Exhibition Block | High | 10 | 1 Dev | CUSTOM: Interactive virtual tour/3D
|  | Subtotal - LED Custom Blocks |  | 40
|  | TOTAL LED BLOCK DEVELOPMENT (11 blocks) |  | 64
LED CONTENT MIGRATION
L3.1 |  | LED Import Script Customization | Medium | 5 | 1 Dev | LED-specific parsers
L3.2 |  | LED Product Pages (20+ pages × 6 regions) | Medium | 10 | 1 Dev + 1 Content | All product lines, regional variants
L3.3 |  | LED Application Pages (10+ pages) | Medium | 5 | 1 Content | Lighting, Auto, Display
L3.4 |  | LED Support & Tools Pages | Medium | 4 | 1 Content | Calculators, downloads
L3.5 |  | LED News & Events | Low | 3 | 1 Content | Articles, exhibitions
L3.6 |  | LED Asset Migration | Medium | 5 | 1 Dev | Product images, datasheets
L3.7 |  | LED URL Redirects | Low | 3 | 1 Dev | led.samsung.com mapping
|  | Subtotal - Content Migration |  | 35
LED INTEGRATIONS & TESTING
L4.1 |  | LED Regional Support (6 regions) | High | 8 | 1 Dev | America, EMEA, CN, SEA, JP, KR
L4.2 |  | LED Calculator Validation & Testing | High | 8 | 1 QA | Calculator accuracy, cross-browser
L4.3 |  | LED Performance Optimization | Medium | 4 | 1 Dev | Calculator load performance
L4.4 |  | LED Content QA (6 regions) | Medium | 6 | 1 QA | Visual regression per region
|  | Subtotal - Integrations & Testing |  | 26
| GRAND TOTAL — LED INCREMENTAL (REVISED v3.0) |  |  | 136 |  | ~5-6 additional weeks

## Combined Summary
Migration Effort Summary — REVISED v3.0 (Samsung Internal Data)
31,603 pages ¦ 643 components ¦ 229GB DAM ¦ 9 regions ¦ 6 OSGi bundles
Work Stream | Semi Only (Days) | LED Incr. (Days) | Combined (Days) | Combined (Weeks)
Discovery & Architecture | 66 | 11 | 77 | 3.5
Foundation & Setup | 77 | — | 77 | 3.5
Block Development — Reuse (style only) | 27 | 7 | 34 | 1.5
Block Development — Extend (customize) | 59 | 17 | 76 | 3.5
Block Development — Custom (new build) | 88 | 40 | 128 | 6
External Services & API Layer (OSGi replacement) | 95 | — | 95 | 4.5
Content & Asset Migration (31K pages + 229GB) | 173 | 35 | 208 | 9.5
Integrations | 36 | — | 36 | 1.5
Testing & QA (9 regions × 4 locales) | 95 | 26 | 121 | 5.5
Launch & Handover (staged regional cutover) | 41 | — | 41 | 2
TOTAL — Semiconductor Only | 757 | — | 757 | ~9-11 months
TOTAL — LED Incremental | — | 136 | 136 | ~5-6 weeks
TOTAL — Combined (Semi + LED) | 757 | 136 | 893 | ~11-14 months
ESTIMATE EVOLUTION — Why this differs from initial assessment
Metric | Initial (Web crawl) | Samsung Actual | Impact
Total Pages | 350-500 (estimated) | 31,603 (confirmed) | 90x more pages → content migration 3x effort
Components | 25-35 blocks | 643 nodes / 132+ types | Must consolidate 643→33 EDS blocks
Regions | 4 assumed | 9 confirmed | 2.25x validation/testing matrix
Templates | 7-9 estimated | 44 WCM + 6 types | Complex template consolidation effort
OSGi Bundles | Not assessed | 6 custom + 3 third-party | NEW: API externalization layer needed
Admin UIs | Not assessed | 5 custom UIs | NEW: Separate headless admin apps
External DB | Not assessed | MySQL direct JDBC | NEW: REST microservice required
CDN/Storage | Not assessed | Akamai NetStorageKit | NEW: CDN migration/replacement
COST ESTIMATION (Based on Adobe Professional Services Rates) — REVISED v3.0
Scenario | Person-Days | Team Size | Duration | Est. Cost Range (USD)
Semiconductor Only | 757 | 5-7 FTEs | 9-11 months | $1.32M - $1.67M
LED Only (standalone*) | 420 | 3-4 FTEs | 6-8 months | $735K - $925K
Combined (Semi + LED) | 893 | 6-8 FTEs | 11-14 months | $1.56M - $1.96M
* LED standalone includes shared foundation/API effort absorbed in combined scenario
Cost based on blended rate of $1,750-$2,200/day for Adobe Professional Services
Samsung's own assessment: Large category, 9-12 months (aligns with our Semiconductor-only estimate)

## Risk Register
Risk Register (Revised v3.0 — from Samsung analysis)
ID | Risk Description | Likelihood | Impact | Mitigation Strategy | Owner
R1 | MySQL direct JDBC → Cloud/EDS has no JDBC support | Confirmed | High | Externalize to REST microservice; AEM uses API calls only | Backend Dev
R2 | DAM 224GB single tree (98%) — migration throughput | High | High | CTT chunk split + top-up rounds; pre-cleanup unused assets | DevOps
R3 | Akamai NetStorageKit dependency | Confirmed | High | Migrate to Cloud Manager CDN or EDS native delivery | DevOps
R4 | 5 Custom Admin UIs (PIM, privacy, terms, site-ia, tasks) | Confirmed | High | Granite/Coral UI audit; externalize as SPA or headless apps | Architect
R5 | 9 regions × 4 locales simultaneous operation | Confirmed | High | Region-by-region cutover; automated validation (Playwright) | PM
R6 | 31,603 pages content migration volume | Confirmed | High | Automated import scripts per region; parallel processing | Content Eng
R7 | semi-common 1.7MB core bundle → externalization | High | High | Priority #1 refactoring; AEM Cloud SDK API compatibility matrix | Tech Lead
R8 | 643 components consolidated to 33 EDS blocks | Medium | High | POC key blocks in Phase 1; validate mapping assumptions early | Architect
R9 | 44 WCM templates + 6 types → 8-10 EDS templates | Medium | Medium | Template consolidation workshop; validate with content teams | Architect
R10 | JSP 9 remaining (admin/taskmanagement) | Confirmed | Low | HTL conversion (small scope) or externalize to admin SPA | Dev
R11 | DAM 1.69M nodes / 8.8M props — index performance | Medium | Medium | Oak Index redesign; metadata cleanup before migration | DevOps
R12 | LED calculator tools complexity | Medium | High | Dedicated spike/POC; third-party widget as fallback | Tech Lead
R13 | SEO ranking impact — 31,603 URL redirects | High | High | Comprehensive redirect map; staged rollout; 90-day monitoring | SEO
R14 | Repository structure not modernized (ui.apps/ui.content) | Confirmed | Medium | Apply Repository Modernizer before migration | Dev

## Resource Plan
Recommended Team Structure (Combined Semi + LED)
Role | Count | Responsibilities | Duration
Solution Architect | 1 | Component mapping (643→33), template strategy, integration architecture | Full duration
Senior EDS Developer | 2 | Block development (extend/custom), EDS patterns, performance | Full duration
Backend Developer | 1 | MySQL API service, OSGi externalization, serverless functions | Months 2-8
Frontend Developer | 1-2 | Block styling (reuse tier), 254 CSS migration, responsive, a11y | Months 2-10
Content/DAM Engineer | 1-2 | DAM audit (229GB), 31K page migration, import scripts, per-region QA | Months 4-12
QA Engineer | 1-2 | 9-region testing, accessibility, cross-browser, integration tests | Months 6-14
Project Manager | 1 | Region cutover planning, stakeholder coordination, training | Full duration
UX Designer | 0.5 | Design system extraction from 582 JS / 254 CSS | Months 1-3
DevOps Engineer | 1 | CDN migration, Akamai replacement, CI/CD, DAM migration tooling | Months 2-6, 10-14
Total Team: 6-8 FTEs at peak (months 4-10)
Ramp: Start with 4, scale to 8 at month 4, taper to 4 from month 10

## Timeline
Project Timeline — Combined (REVISED v3.0)
11-14 months ¦ Staged regional cutover
Phase / Activity | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14
Phase 1: Discovery & Architecture | bar: M1 to M2
Phase 2: Foundation & Setup | bar: M2 to M4
Phase 3a: Block Reuse (style only) | bar: M3 to M4
Phase 3b: Block Extend (customize) | bar: M3 to M6
Phase 3c: Block Custom (Semi + LED) | bar: M4 to M9
Phase 4: External Services / API Layer | bar: M3 to M8
Phase 5a: DAM Audit & Asset Migration | bar: M4 to M8
Phase 5b: Content Migration (31K pages) | bar: M5 to M11
Phase 6: Integrations | bar: M6 to M8
Phase 7: Testing & QA (per region) | bar: M7 to M12
Phase 8: UAT — ssir/de cutover | bar: M9 to M10
Phase 9: UAT — kr/jp cutover | bar: M10 to M11
Phase 10: UAT — cn/us/emea cutover | bar: M11 to M12
Phase 11: UAT — global cutover + hypercare | bar: M12 to M14
Staged Regional Cutover Strategy (from Samsung analysis):
ssir/de (small, low risk) → kr/jp → cn → us/emea → global (master, highest risk last)